## Slide 1: Cost Estimation Methology & Budget
Cost estimation was based on:
Analogous estimating
Expert judgment
Bottom-up estimation based on the WBS
A 10% contingency reserve for unexpected costs and campaign adjustments
€2,805 Budget at Completion
€2,550 Project Costs
€255 Contingency Reserve

## Slide 2: Project Cost Baseline
Chart: Cost Breakdown by Work Package
| Paid Advertising | Content Creation | Strategy Development | Project Management | Monitoring & Control | Airbnb Optimization | Final Evaluation
cost (€) | 900 | 550 | 300 | 250 | 250 | 150 | 150
SUBTOTAL €2,550 CONTINGENGY €255 (10%) BAC €2,805

## Slide 3: Time-Phased Cost Baseline Planned project expenditure from April to October 2026
Chart: 
| 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Cumulative Project Cost | 700 | 1550 | 1900 | 2150 | 2400 | 2805 | 2805
🟨 Key Insight April and May account for the highest share of project expenditure, covering research, strategy, content creation and campaign preparation.

## Slide 4: Financial Justification
Occupancy Improvement
45% Current Off-Season Occupancy
65% Target Off-Season Occupancy
€4,800
Expected Additional Annual Income
Financial Return
€2,805 Project Investment (BAC)
€1,995 Expected Net Benefit
71% Return on Investment (ROI)
Positive Financial Outlook The expected annual benefit exceeds the total project investment.

## Slide 5: Risk Management Plan Managing Uncertainty through an Agile approach
OBJECTIVE
Manage uncertainties affecting the achievement of the 65% off-season occupancy target.
IDENTIFY ASSESS MITIGATE MONITOR
KEY INPUTS
Historical data , Platforms Analytics, Competitor Research, Stakeholder Feedback
€255
CONTINGENCY RESERVE
10% OF TOTAL BUDGET

## Slide 6: Key Project Risks
Five Key Risk Categories ​
Responsibilities
Risk Identification — Product Owner • Risk Assessment — Digital Marketing Specialist • Agile Monitoring — All Team Members
Continuous monitoring throughout every 2-week sprint
PLATFORM
Algorithm & availability
Changes
CONTENT
Low engagement & conversion
FINANCIAL
Campaign costs may exceed budget
ADOPTION
Delayed approvals
PERFORMANCE
Occupancy below 65%

## Slide 7: Probability & Impact Matrix Risk Response Framework
Probability / Impact | LOW | MEDIUM | HIGH
HIGH 81-100% | Monitoring | Mitigation | Avoid / Redesign Performance Risk
MEDIUM 41-80% | Monitoring | Mitigation Content Risk Αdoption Risk | Transfer / Plan B Platform Risk Financial Risk
LOW 0-40% | Acceptance | Acceptance | Active Monitoring
Risk Priority
Performance Risk is the highest-priority risk and requires immediate management attention and corrective action.